## Sheet1
Time and Effort Matrix
Task list | Start Date | End Data | Effort (1 = 1 hour per person) | Assignee | Effort
Specify and design system architecture | 2024-09-19 | 2024-09-26 | 3 | Whole team
Specify and design data model | 2024-09-26 | 2024-10-10 | 3 | Whole team
Research and document database software and data storage | 2024-10-10 | 2024-10-24 | 6 | Whole team
Research and document application and user interface framework | 2024-10-10 | 2024-10-24 | 5 | Travis
Research and document AI/Automated bot integration | 2024-10-10 | 2024-10-24 | 5 | Simon
Design database software and data storage tables | 2024-10-24 | 2024-10-31 | 8 | Gabe
Design and specify application user actions | 2024-10-24 | 2024-10-31 | 8 | Travis
Design and specify admin view of application | 2024-10-24 | 2024-10-31 | 8 | Simon
Develop application user interface(euchre game only) | 2024-10-31 | 2024-12-14 | 24 | Travis
Develop database and data storage tables | 2024-10-31 | 2024-12-14 | 16 | Gabe
Develop probability calculations from database tables | 2024-10-31 | 2024-12-14 | 14 | Gabe
Develop admin view for application with views of relevant data | 2024-10-31 | 2025-03-14 | 8 | Simon, Travis
Develop AI/automated bot for initial euchre game | 2024-10-31 | 2025-03-14 | 24 | Simon
Validate working model for initial euchre game | 2024-12-14 | 2025-01-12 | 10 | Whole team
Validate correct data transferred to database | 2024-12-14 | 2025-01-12 | 10 | Gabe
Validate correct data returned from database to user interface | 2024-12-14 | 2025-01-12 | 12 | Gabe
Validate correctness of AI / automated bot actions for initial euchre game | 2025-01-13 | 2025-03-14 | 10 | Simon
Develop overlay for probability calculations | 2025-01-13 | 2025-03-14 | 16 | Travis
Refine AI/automated bot actions to increase probablility outcomes | 2025-03-14 | 2025-03-28 | 12 | Simon
Refine user interface to include additional features | 2025-03-14 | 2025-03-28 | 10 | Travis
Refine admin view to give more value to data | 2025-03-14 | 2025-03-28 | 14 | Simon, Gabe
Milestones | End Date
Research for all components is completed (Tasks 1-5) | 2024-10-24
Design specifications are completed and development has been started (Tasks 6-8) | 2024-10-31
Initial development is complete and Initial euchre game is in a working state (Tasks 9-12) | 2025-01-12
Initial AI has been developed and ready for testing (Task 13) | 2025-03-14
Initial overlay of probabilites is added to the UI (Task 18) | 2025-03-14
Refine and validate (Tasks 14-17, 19-21) | 2025-03-28
Completed euchre game | 2025-04-04